## Dashboard
DualThread — System Acceptance Test Report
Generated 2026-10-30T12:53:14+05:30 ¦ Mode: full ¦ Project: C:\Users\Asus\OneDrive\Documents\Default Project\DualThread
GATE |  | TOTAL CHECKS |  | PASS RATE |  | FAILED | WARNINGS
PASS |  | 163 |  | 98.77% |  | 0 | 2
EXECUTIVE SUMMARY
Files inspected | 120
File-level failures | 0
File-level warnings | 0
Skipped checks | 0
Run started | 2026-10-30T12:51:41+05:30
Run finished | 2026-10-30T12:53:14+05:30
Duration (seconds) | 92.8
Git revision | 135c642
Git branch | main
Working tree | dirty
RESULTS BY PHASE
Phase | Passed | Failed | Warnings | Skipped | Total
ACCEPTANCE | 17 | 0 | 0 | 0 | 17
BUILD | 7 | 0 | 0 | 0 | 7
ENVIRONMENT | 10 | 0 | 1 | 0 | 11
FILE INVENTORY | 9 | 0 | 0 | 0 | 9
INTEGRATION | 40 | 0 | 0 | 0 | 40
REPORT | 1 | 0 | 0 | 0 | 1
STATIC ANALYSIS | 5 | 0 | 1 | 0 | 6
STRUCTURE | 30 | 0 | 0 | 0 | 30
UNIT TESTS | 42 | 0 | 0 | 0 | 42
TOP DEFECTS
ID | Status | Severity | Phase | Test | File | Remediation
STA-006 | WARN | major | STATIC ANALYSIS | No plaintext production credentials in source or configuration |  | Move credentials to environment variables or a secret store before production use.
ENV-011 | WARN | minor | ENVIRONMENT | Working tree is clean before testing |  | Commit or stash changes before a release run.
How to read this workbook: Test Cases contains every executed check; File Inventory proves every tracked file was inspected; Defects is the actionable queue for the auto-healer agent; Traceability maps requirements to code and runtime evidence.

## Test Cases
Test Cases
Every check executed by the SAT agent, with evidence and remediation.
Test ID | Phase | Test | Category | Severity | Status | Duration (ms) | Details | Evidence | File | Line | Error Type | Remediation | Owner | Tags | Timestamp
ENV-001 | ENVIRONMENT | Host is Windows x64 | environment | major | PASS | 0 | Windows 11 (AMD64) | [5 empty] | sat-tester | environment, os | 2026-10-30T12:51:41+05:30
ENV-002 | ENVIRONMENT | Python 3.10+ is available | environment | major | PASS | 0 | 3.13.15 |  |  |  | python-version | Install Python 3.10 or newer. | sat-tester | environment, python | 2026-10-30T12:51:41+05:30
ENV-003 | ENVIRONMENT | openpyxl is installed for Excel reporting | environment | critical | PASS | 0 | 3.1.5 |  |  |  | openpyxl-missing | Run: py -3 -m pip install openpyxl | sat-tester | environment, excel | 2026-10-30T12:51:41+05:30
ENV-004 | ENVIRONMENT | Visual Studio MSBuild is available | environment | critical | PASS | 0 | C:\Program Files\Microsoft Visual Studio\18\Community\MSBuild\Current\Bin\MSBuild.exe |  |  |  | msbuild-missing | Install Visual Studio with Desktop development with C++. | sat-tester | environment, build | 2026-10-30T12:51:41+05:30
ENV-005 | ENVIRONMENT | vcpkg dependencies hiredis and librdkafka are installed | environment | critical | PASS | 0 | vcpkg=C:\vcpkg; hiredis.lib=yes, rdkafka.lib=yes |  |  |  | vcpkg-missing | Run: vcpkg install hiredis:x64-windows librdkafka:x64-windows | sat-tester | environment, build, dependencies | 2026-10-30T12:51:41+05:30
ENV-006 | ENVIRONMENT | MySQL is available on port 3306 | environment | major | PASS | 0 | Listening. |  |  |  | dependency-offline | Start the dependency before running the full integration suite. | sat-tester | environment, dependency | 2026-10-30T12:51:42+05:30
ENV-007 | ENVIRONMENT | Redis/Memurai is available on port 6379 | environment | major | PASS | 0 | Listening. |  |  |  | dependency-offline | Start the dependency before running the full integration suite. | sat-tester | environment, dependency | 2026-10-30T12:51:42+05:30
ENV-008 | ENVIRONMENT | Kafka is available on port 9092 | environment | major | PASS | 0 | Listening. |  |  |  | dependency-offline | Start the dependency before running the full integration suite. | sat-tester | environment, dependency | 2026-10-30T12:51:42+05:30
ENV-009 | ENVIRONMENT | At least 2 GB of free disk space is available | environment | major | PASS | 0 | 249.7 GB free |  |  |  | disk-space | Free disk space before building. | sat-tester | environment, disk | 2026-10-30T12:51:42+05:30
ENV-010 | ENVIRONMENT | Git revision is recorded for the test run | environment | info | PASS | 0 | main@135c642; dirty=True; remote=https://github.com/Tamilselvan-19/DualThread.git | [5 empty] | sat-tester | environment, git | 2026-10-30T12:51:43+05:30
ENV-011 | ENVIRONMENT | Working tree is clean before testing | environment | minor | WARN | 0 | Uncommitted changes are present; the report describes the working tree, not a tagged commit. |  |  |  | dirty-tree | Commit or stash changes before a release run. | sat-tester | environment, git | 2026-10-30T12:51:43+05:30
INV-001 | FILE INVENTORY | Inventory discovered and hashed every tracked file (120) | functional | major | PASS | 0 | 120 files inspected. SHA-256, size, category, line count and encoding recorded. | File Inventory sheet |  |  |  |  | sat-tester | inventory, coverage | 2026-10-30T12:51:44+05:30
INV-002 | FILE INVENTORY | All files are readable | quality | critical | PASS | 0 | No issues. | File Inventory sheet |  |  | inventory-unreadable | Repair file permissions or remove the unreadable file. | sat-tester | inventory, unreadable | 2026-10-30T12:51:44+05:30
INV-003 | FILE INVENTORY | No source, config, database, script or documentation file is empty | quality | major | PASS | 0 | No issues. | File Inventory sheet |  |  | inventory-empty | Restore the file content or delete the placeholder and update references. | sat-tester | inventory, empty | 2026-10-30T12:51:44+05:30
INV-004 | FILE INVENTORY | Text files are valid UTF-8 | quality | minor | PASS | 0 | No issues. | File Inventory sheet |  |  | inventory-encoding | Convert the file to UTF-8 without BOM. | sat-tester | inventory, encoding | 2026-10-30T12:51:44+05:30
INV-005 | FILE INVENTORY | No merge conflict markers remain | quality | critical | PASS | 0 | No issues. | File Inventory sheet |  |  | inventory-conflict | Resolve the merge conflict and rebuild. | sat-tester | inventory, conflict | 2026-10-30T12:51:44+05:30
INV-006 | FILE INVENTORY | No unexpected UTF-8 BOM | quality | minor | PASS | 0 | No issues. | File Inventory sheet |  |  | inventory-bom | Save the file as UTF-8 without BOM. | sat-tester | inventory, bom | 2026-10-30T12:51:44+05:30
INV-007 | FILE INVENTORY | Binary artifacts have valid PE/image/PDF signatures | quality | major | PASS | 0 | No issues. | File Inventory sheet |  |  | inventory-binary_signature | Replace the corrupt binary or rebuild it from source. | sat-tester | inventory, binary_signature | 2026-10-30T12:51:44+05:30
INV-008 | FILE INVENTORY | All tracked files have a known extension | quality | minor | PASS | 0 | No issues. | File Inventory sheet |  |  | inventory-extension | Confirm the file is intentional and add it to the inventory exclusions if generated. | sat-tester | inventory, extension | 2026-10-30T12:51:44+05:30
INV-009 | FILE INVENTORY | Every C/C++ source file belongs to a build target | coverage | minor | PASS | 0 | No issues. | File Inventory sheet |  |  | inventory-coverage | Add the source to its project or remove the dead file. | sat-tester | inventory, coverage, source | 2026-10-30T12:51:44+05:30
STR-001 | STRUCTURE | All required project, config, database and script files exist | completeness | critical | PASS | 0 | No issues. |  |  |  | missing-file | Restore the missing file before building or releasing. | sat-tester | structure, files | 2026-10-30T12:51:44+05:30
STR-002 | STRUCTURE | Solution file is present and lists all four projects | build-system | critical | PASS | 0 | Projects: chatclient, chatserver, dbwriter, loadbalancer. |  | CppChatMessaging.sln |  | solution-structure | Restore the project entry and file path in the solution. | sat-tester | structure, solution | 2026-10-30T12:51:44+05:30
STR-003 | STRUCTURE | ChatClient/ChatClient.vcxproj references existing sources and defines Release¦x64 | build-system | major | PASS | 0 | 26 source/header references. Release¦x64 present. Platform toolset set. |  | ChatClient/ChatClient.vcxproj |  | project-reference | Add the missing source files or fix the project configuration. | sat-tester | structure, vcxproj | 2026-10-30T12:51:44+05:30
STR-004 | STRUCTURE | ChatServer/ChatServer.vcxproj references existing sources and defines Release¦x64 | build-system | major | PASS | 0 | 25 source/header references. Release¦x64 present. Platform toolset set. |  | ChatServer/ChatServer.vcxproj |  | project-reference | Add the missing source files or fix the project configuration. | sat-tester | structure, vcxproj | 2026-10-30T12:51:45+05:30
STR-005 | STRUCTURE | DBWriter/DBWriter.vcxproj references existing sources and defines Release¦x64 | build-system | major | PASS | 0 | 15 source/header references. Release¦x64 present. Platform toolset set. |  | DBWriter/DBWriter.vcxproj |  | project-reference | Add the missing source files or fix the project configuration. | sat-tester | structure, vcxproj | 2026-10-30T12:51:45+05:30
STR-006 | STRUCTURE | LoadBalancer/LoadBalancer.vcxproj references existing sources and defines Release¦x64 | build-system | major | PASS | 0 | 17 source/header references. Release¦x64 present. Platform toolset set. |  | LoadBalancer/LoadBalancer.vcxproj |  | project-reference | Add the missing source files or fix the project configuration. | sat-tester | structure, vcxproj | 2026-10-30T12:51:45+05:30
STR-007 | STRUCTURE | config/server1.ini contains all required keys | configuration | critical | PASS | 0 | No issues. |  | config/server1.ini |  | config-keys | Add the missing keys using the documented defaults. | sat-tester | structure, config | 2026-10-30T12:51:45+05:30
STR-008 | STRUCTURE | config/server2.ini contains all required keys | configuration | critical | PASS | 0 | No issues. |  | config/server2.ini |  | config-keys | Add the missing keys using the documented defaults. | sat-tester | structure, config | 2026-10-30T12:51:45+05:30
STR-009 | STRUCTURE | config/loadbalancer.ini contains all required keys | configuration | critical | PASS | 0 | No issues. |  | config/loadbalancer.ini |  | config-keys | Add the missing keys using the documented defaults. | sat-tester | structure, config | 2026-10-30T12:51:45+05:30
STR-010 | STRUCTURE | config/dbwriter.ini contains all required keys | configuration | critical | PASS | 0 | No issues. |  | config/dbwriter.ini |  | config-keys | Add the missing keys using the documented defaults. | sat-tester | structure, config | 2026-10-30T12:51:45+05:30
STR-011 | STRUCTURE | config/client.ini contains all required keys | configuration | critical | PASS | 0 | No issues. |  | config/client.ini |  | config-keys | Add the missing keys using the documented defaults. | sat-tester | structure, config | 2026-10-30T12:51:45+05:30
STR-012 | STRUCTURE | load balancer backend1 TCP matches server1 | configuration | major | PASS | 0 | Observed: 6001 vs 6001 |  |  |  | config-mismatch | Align the ports, topic, brokers and database names across all configs. | sat-tester | structure, config, consistency | 2026-10-30T12:51:45+05:30
STR-013 | STRUCTURE | load balancer backend1 UDP matches server1 | configuration | major | PASS | 0 | Observed: 7001 vs 7001 |  |  |  | config-mismatch | Align the ports, topic, brokers and database names across all configs. | sat-tester | structure, config, consistency | 2026-10-30T12:51:45+05:30
STR-014 | STRUCTURE | load balancer backend2 TCP matches server2 | configuration | major | PASS | 0 | Observed: 6002 vs 6002 |  |  |  | config-mismatch | Align the ports, topic, brokers and database names across all configs. | sat-tester | structure, config, consistency | 2026-10-30T12:51:45+05:30
STR-015 | STRUCTURE | load balancer backend2 UDP matches server2 | configuration | major | PASS | 0 | Observed: 7002 vs 7002 |  |  |  | config-mismatch | Align the ports, topic, brokers and database names across all configs. | sat-tester | structure, config, consistency | 2026-10-30T12:51:45+05:30
STR-016 | STRUCTURE | client TCP port matches load balancer | configuration | major | PASS | 0 | Observed: client vs balancer |  |  |  | config-mismatch | Align the ports, topic, brokers and database names across all configs. | sat-tester | structure, config, consistency | 2026-10-30T12:51:45+05:30
STR-017 | STRUCTURE | client UDP port matches load balancer | configuration | major | PASS | 0 | Observed: client vs balancer |  |  |  | config-mismatch | Align the ports, topic, brokers and database names across all configs. | sat-tester | structure, config, consistency | 2026-10-30T12:51:45+05:30
STR-018 | STRUCTURE | both servers use the same Kafka topic | configuration | major | PASS | 0 | Observed: chat-messages |  |  |  | config-mismatch | Align the ports, topic, brokers and database names across all configs. | sat-tester | structure, config, consistency | 2026-10-30T12:51:45+05:30
STR-019 | STRUCTURE | both servers use the same Kafka brokers | configuration | major | PASS | 0 | Observed: brokers |  |  |  | config-mismatch | Align the ports, topic, brokers and database names across all configs. | sat-tester | structure, config, consistency | 2026-10-30T12:51:45+05:30
STR-020 | STRUCTURE | both servers use the same MySQL database | configuration | major | PASS | 0 | Observed: ChatDatabase |  |  |  | config-mismatch | Align the ports, topic, brokers and database names across all configs. | sat-tester | structure, config, consistency | 2026-10-30T12:51:45+05:30
STR-021 | STRUCTURE | server IDs are distinct | configuration | major | PASS | 0 | Observed: server1 / server2 |  |  |  | config-mismatch | Align the ports, topic, brokers and database names across all configs. | sat-tester | structure, config, consistency | 2026-10-30T12:51:45+05:30
STR-022 | STRUCTURE | server TCP/UDP ports are distinct | configuration | major | PASS | 0 | Observed: 6001,7001,6002,7002 |  |  |  | config-mismatch | Align the ports, topic, brokers and database names across all configs. | sat-tester | structure, config, consistency | 2026-10-30T12:51:45+05:30
STR-023 | STRUCTURE | Database schema defines every table and column used by the code | database | critical | PASS | 0 | No issues. |  | database/schema.sql |  | schema-mismatch | Update schema.sql and apply the migration before testing persistence. | sat-tester | database, schema | 2026-10-30T12:51:45+05:30
STR-024 | STRUCTURE | MessageId uniqueness guard is present in the chat table | database | major | PASS | 0 | UNIQUE constraint found. |  | database/schema.sql |  | schema-guard | Add UNIQUE(MessageId) to preserve at-least-once Kafka delivery semantics. | sat-tester | database, schema, idempotency | 2026-10-30T12:51:45+05:30
STR-025 | STRUCTURE | Documentation links and images resolve | documentation | minor | PASS | 0 | No broken links. |  |  |  | broken-doc-link | Fix or remove the broken relative link. | sat-tester | docs, links | 2026-10-30T12:51:45+05:30
STR-026 | STRUCTURE | README documents build, run, test and configuration | documentation | minor | PASS | 0 | All sections present. |  | README.md |  | doc-coverage | Add the missing operational section to README.md. | sat-tester | docs, readme | 2026-10-30T12:51:45+05:30
STR-027 | STRUCTURE | scripts/start-all.ps1 parses without PowerShell syntax errors | automation | major | PASS | 0 | No syntax errors. |  | scripts/start-all.ps1 |  | powershell-syntax | Fix the PowerShell parser error. | sat-tester | structure, scripts | 2026-10-30T12:51:47+05:30
STR-028 | STRUCTURE | scripts/stop-all.ps1 parses without PowerShell syntax errors | automation | major | PASS | 0 | No syntax errors. |  | scripts/stop-all.ps1 |  | powershell-syntax | Fix the PowerShell parser error. | sat-tester | structure, scripts | 2026-10-30T12:51:48+05:30
STR-029 | STRUCTURE | Build outputs, logs and generated reports are git-ignored | quality | minor | PASS | 0 | No issues. |  | .gitignore |  | gitignore | Add the generated paths to .gitignore. | sat-tester | structure, git | 2026-10-30T12:51:48+05:30
STR-030 | STRUCTURE | vcpkg manifest declares native dependencies | build-system | critical | PASS | 0 | hiredis and librdkafka declared. |  | vcpkg.json |  | vcpkg-manifest | Declare hiredis and librdkafka in vcpkg.json. | sat-tester | structure, dependencies | 2026-10-30T12:51:48+05:30
STA-001 | STATIC ANALYSIS | Worker threads marshal UI updates through PostMessage | thread-safety | major | PASS | 0 | PostMessage is used for cross-thread UI notifications. |  | ChatClient/ChatSession.cpp |  | thread-ui | Use PostMessage and handle the work on the UI thread; never touch MFC controls from a worker. | sat-tester | static, threads, mfc | 2026-10-30T12:51:49+05:30
STA-002 | STATIC ANALYSIS | Protocol enforces the documented 16 MiB frame limit | protocol | critical | PASS | 0 | MAX_FRAME_SIZE is 16 MiB. |  | Common/Protocol.cpp |  | protocol-limit | Keep MAX_FRAME_SIZE at 16 MiB and enforce it before allocation. | sat-tester | static, protocol | 2026-10-30T12:51:49+05:30
STA-003 | STATIC ANALYSIS | Server enforces the documented 8000-character message limit | protocol | major | PASS | 0 | kMaxMessageLength is 8000. |  | ChatServer/TcpServer.cpp |  | message-limit | Restore the 8000-character limit or update the documented contract. | sat-tester | static, protocol | 2026-10-30T12:51:49+05:30
STA-004 | STATIC ANALYSIS | No source file is excessively large (>2500 lines) | maintainability | info | PASS | 0 | No oversized files. |  |  |  | large-file | Split the file into focused units. | sat-tester | static, maintainability | 2026-10-30T12:51:49+05:30
STA-005 | STATIC ANALYSIS | Automation tooling compiles as Python 3 | automation | critical | PASS | 0 | No syntax errors. |  |  |  | python-syntax | Fix the Python syntax error in the test tooling. | sat-tester | static, python | 2026-10-30T12:51:49+05:30
STA-006 | STATIC ANALYSIS | No plaintext production credentials in source or configuration | security | major | WARN | 0 | Demo credentials are present (expected for this assessment build): config/dbwriter.ini: value=T*******% config/server1.ini: value=T*******% config/server2.ini: value=T*******% |  |  |  | plaintext-secret | Move credentials to environment variables or a secret store before production use. | sat-tester | static, security, secrets | 2026-10-30T12:51:49+05:30
BLD-001 | BUILD | Running application processes are stopped before rebuild | build | info | PASS | 0 | Stopped: ChatServer:23624, ChatServer:24684, LoadBalancer:20532, DBWriter:9680 Hydrated 15 build artifacts. | [5 empty] | sat-tester | build, process | 2026-10-30T12:51:52+05:30
BLD-002 | BUILD | MSBuild is available | build | critical | PASS | 0 | C:\Program Files\Microsoft Visual Studio\18\Community\MSBuild\Current\Bin\MSBuild.exe | [5 empty] | sat-tester | build, toolchain | 2026-10-30T12:51:52+05:30
BLD-003 | BUILD | Release¦x64 solution build succeeds | build | critical | PASS | 42892 | Exit code 0; 0 errors, 5 warnings. | reports/logs/build-20261030-125235.log |  |  | build |  | sat-tester | build, msbuild | 2026-10-30T12:52:35+05:30
BLD-004 | BUILD | Build warnings stay below the configured threshold | quality | minor | PASS | 0 | 5 warnings (threshold 250). | reports/logs/build-20261030-125235.log |  |  | build-warnings | Reduce warnings, especially C4244/C4309, in project-owned code. | sat-tester | build, quality | 2026-10-30T12:52:35+05:30
BLD-005 | BUILD | First-party code compiles without warnings | quality | minor | PASS | 0 | No warnings from project-owned files. | reports/logs/build-20261030-125235.log |  |  |  |  | sat-tester | build, warnings | 2026-10-30T12:52:35+05:30
BLD-006 | BUILD | All required executables and runtime DLLs are present and valid PE files | build | critical | PASS | 0 | 7/7 artifacts; all x64 PE files. | Release Manifest sheet |  |  | artifact-missing | Rebuild or restore the missing runtime dependency. | sat-tester | build, artifacts | 2026-10-30T12:52:35+05:30
BLD-007 | BUILD | Release binaries are newer than the source tree | release | major | PASS | 0 | Artifacts are current. |  |  |  | stale-artifact | Run the release agent to rebuild and stage fresh binaries. | sat-tester | build, release | 2026-10-30T12:52:35+05:30
UNT-001 | UNIT TESTS | Unit test binary compiles against the real Common sources | build | critical | PASS | 12055 | test_common.cpp linked with JsonUtil.cpp, Sha256.cpp, Ini.cpp and Protocol.cpp. | reports/work/unit-build.log |  |  |  |  | sat-tester | unit, compile | 2026-10-30T12:52:47+05:30
UNT-002 | UNIT TESTS | Common::json escape plain | unit | major | PASS | 0 | json_escape_plain passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_escape_plain | 2026-10-30T12:52:47+05:30
UNT-003 | UNIT TESTS | Common::json escape quote | unit | major | PASS | 0 | json_escape_quote passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_escape_quote | 2026-10-30T12:52:47+05:30
UNT-004 | UNIT TESTS | Common::json escape backslash | unit | major | PASS | 0 | json_escape_backslash passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_escape_backslash | 2026-10-30T12:52:47+05:30
UNT-005 | UNIT TESTS | Common::json escape controls | unit | major | PASS | 0 | json_escape_controls passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_escape_controls | 2026-10-30T12:52:47+05:30
UNT-006 | UNIT TESTS | Common::json escape low control | unit | major | PASS | 0 | json_escape_low_control passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_escape_low_control | 2026-10-30T12:52:47+05:30
UNT-007 | UNIT TESTS | Common::json parse roundtrip | unit | major | PASS | 0 | {"type":"chat","message":"hello \"world\"\nline2","count":"42","flag":"true","empty":""} |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_parse_roundtrip | 2026-10-30T12:52:47+05:30
UNT-008 | UNIT TESTS | Common::json parse type | unit | major | PASS | 0 | json_parse_type passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_parse_type | 2026-10-30T12:52:47+05:30
UNT-009 | UNIT TESTS | Common::json parse escaped message | unit | major | PASS | 0 | json_parse_escaped_message passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_parse_escaped_message | 2026-10-30T12:52:47+05:30
UNT-010 | UNIT TESTS | Common::json get int | unit | major | PASS | 0 | json_get_int passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_get_int | 2026-10-30T12:52:47+05:30
UNT-011 | UNIT TESTS | Common::json get bool | unit | major | PASS | 0 | json_get_bool passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_get_bool | 2026-10-30T12:52:47+05:30
UNT-012 | UNIT TESTS | Common::json get int default | unit | major | PASS | 0 | json_get_int_default passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_get_int_default | 2026-10-30T12:52:47+05:30
UNT-013 | UNIT TESTS | Common::json get default | unit | major | PASS | 0 | json_get_default passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_get_default | 2026-10-30T12:52:47+05:30
UNT-014 | UNIT TESTS | Common::json parse unicode | unit | major | PASS | 0 | json_parse_unicode passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_parse_unicode | 2026-10-30T12:52:47+05:30
UNT-015 | UNIT TESTS | Common::json parse surrogate pair | unit | major | PASS | 0 | json_parse_surrogate_pair passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_parse_surrogate_pair | 2026-10-30T12:52:47+05:30
UNT-016 | UNIT TESTS | Common::json parse plain | unit | major | PASS | 0 | json_parse_plain passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_parse_plain | 2026-10-30T12:52:47+05:30
UNT-017 | UNIT TESTS | Common::json reject invalid | unit | major | PASS | 0 | json_reject_invalid passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_reject_invalid | 2026-10-30T12:52:47+05:30
UNT-018 | UNIT TESTS | Common::json reject array | unit | major | PASS | 0 | json_reject_array passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, json_reject_array | 2026-10-30T12:52:47+05:30
UNT-019 | UNIT TESTS | Common::sha256 empty | unit | major | PASS | 0 | sha256_empty passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, sha256_empty | 2026-10-30T12:52:47+05:30
UNT-020 | UNIT TESTS | Common::sha256 abc | unit | major | PASS | 0 | sha256_abc passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, sha256_abc | 2026-10-30T12:52:47+05:30
UNT-021 | UNIT TESTS | Common::sha256 quick brown fox | unit | major | PASS | 0 | sha256_quick_brown_fox passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, sha256_quick_brown_fox | 2026-10-30T12:52:47+05:30
UNT-022 | UNIT TESTS | Common::sha256 demo password | unit | major | PASS | 0 | sha256_demo_password passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, sha256_demo_password | 2026-10-30T12:52:47+05:30
UNT-023 | UNIT TESTS | Common::ini read value | unit | major | PASS | 0 | ini_read_value passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, ini_read_value | 2026-10-30T12:52:47+05:30
UNT-024 | UNIT TESTS | Common::ini section case insensitive | unit | major | PASS | 0 | ini_section_case_insensitive passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, ini_section_case_insensitive | 2026-10-30T12:52:47+05:30
UNT-025 | UNIT TESTS | Common::ini strip quotes | unit | major | PASS | 0 | ini_strip_quotes passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, ini_strip_quotes | 2026-10-30T12:52:47+05:30
UNT-026 | UNIT TESTS | Common::ini read int | unit | major | PASS | 0 | ini_read_int passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, ini_read_int | 2026-10-30T12:52:47+05:30
UNT-027 | UNIT TESTS | Common::ini read bool | unit | major | PASS | 0 | ini_read_bool passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, ini_read_bool | 2026-10-30T12:52:47+05:30
UNT-028 | UNIT TESTS | Common::ini default int | unit | major | PASS | 0 | ini_default_int passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, ini_default_int | 2026-10-30T12:52:47+05:30
UNT-029 | UNIT TESTS | Common::ini default value | unit | major | PASS | 0 | ini_default_value passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, ini_default_value | 2026-10-30T12:52:47+05:30
UNT-030 | UNIT TESTS | Common::ini missing file | unit | major | PASS | 0 | ini_missing_file passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, ini_missing_file | 2026-10-30T12:52:47+05:30
UNT-031 | UNIT TESTS | Common::queue size | unit | major | PASS | 0 | queue_size passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, queue_size | 2026-10-30T12:52:47+05:30
UNT-032 | UNIT TESTS | Common::queue fifo first | unit | major | PASS | 0 | queue_fifo_first passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, queue_fifo_first | 2026-10-30T12:52:47+05:30
UNT-033 | UNIT TESTS | Common::queue fifo second | unit | major | PASS | 0 | queue_fifo_second passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, queue_fifo_second | 2026-10-30T12:52:47+05:30
UNT-034 | UNIT TESTS | Common::queue wait timeout | unit | major | PASS | 0 | queue_wait_timeout passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, queue_wait_timeout | 2026-10-30T12:52:47+05:30
UNT-035 | UNIT TESTS | Common::queue stop unblocks pop | unit | major | PASS | 0 | 47ms |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, queue_stop_unblocks_pop | 2026-10-30T12:52:47+05:30
UNT-036 | UNIT TESTS | Common::queue concurrent integrity | unit | major | PASS | 0 | consumed=500 |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, queue_concurrent_integrity | 2026-10-30T12:52:47+05:30
UNT-037 | UNIT TESTS | Common::queue clear | unit | major | PASS | 0 | queue_clear passed. |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, queue_clear | 2026-10-30T12:52:47+05:30
UNT-038 | UNIT TESTS | Common::iso timestamp shape | unit | major | PASS | 0 | 2026-10-30T07:22:47Z |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, iso_timestamp_shape | 2026-10-30T12:52:47+05:30
UNT-039 | UNIT TESTS | Common::iso timestamp year | unit | major | PASS | 0 | 2026-10-30T07:22:47Z |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, iso_timestamp_year | 2026-10-30T12:52:47+05:30
UNT-040 | UNIT TESTS | Common::current time shape | unit | major | PASS | 0 | 12:52:47 |  | Common |  | unit-assertion | Correct the shared-library behaviour or the expectation if the contract changed. | auto-healer | unit, current_time_shape | 2026-10-30T12:52:47+05:30
UNT-041 | UNIT TESTS | Unit suite executed without crashes | unit | critical | PASS | 157 | 39 assertions reported, 0 failed. Exit code 0. | reports/work/unit-run.log |  |  | unit | Investigate the assertion failure or crash in the unit log. | auto-healer | unit, execution | 2026-10-30T12:52:47+05:30
UNT-042 | UNIT TESTS | Unit suite covers the shared library contract | coverage | minor | PASS | 0 | 39 assertions executed (target: 20+). | [5 empty] | sat-tester | unit, coverage | 2026-10-30T12:52:47+05:30
INT-001 | INTEGRATION | start-all.ps1 opens the load balancer and both chat servers | environment | critical | PASS | 10637 | 5000=open, 6001=open, 6002=open |  |  |  | service-ports | Inspect logs\*.err.log and the service startup output. | sat-tester | integration, services | 2026-10-30T12:53:00+05:30
INT-002 | INTEGRATION | MySQL is reachable on port 3306 | environment | critical | PASS | 0 | TCP 127.0.0.1:3306 is listening. |  |  |  | dependency-down | Start the dependency and rerun the integration suite. | sat-tester | integration, dependency | 2026-10-30T12:53:00+05:30
INT-003 | INTEGRATION | Redis/Memurai is reachable on port 6379 | environment | critical | PASS | 0 | TCP 127.0.0.1:6379 is listening. |  |  |  | dependency-down | Start the dependency and rerun the integration suite. | sat-tester | integration, dependency | 2026-10-30T12:53:00+05:30
INT-004 | INTEGRATION | Kafka broker is reachable on port 9092 | environment | critical | PASS | 0 | TCP 127.0.0.1:9092 is listening. |  |  |  | dependency-down | Start the dependency and rerun the integration suite. | sat-tester | integration, dependency | 2026-10-30T12:53:00+05:30
INT-005 | INTEGRATION | LoadBalancer TCP is reachable on port 5000 | environment | critical | PASS | 0 | TCP 127.0.0.1:5000 is listening. |  |  |  | dependency-down | Start the dependency and rerun the integration suite. | sat-tester | integration, dependency | 2026-10-30T12:53:00+05:30
INT-006 | INTEGRATION | ChatServer 1 TCP is reachable on port 6001 | environment | critical | PASS | 0 | TCP 127.0.0.1:6001 is listening. |  |  |  | dependency-down | Start the dependency and rerun the integration suite. | sat-tester | integration, dependency | 2026-10-30T12:53:00+05:30
INT-007 | INTEGRATION | ChatServer 2 TCP is reachable on port 6002 | environment | critical | PASS | 0 | TCP 127.0.0.1:6002 is listening. |  |  |  | dependency-down | Start the dependency and rerun the integration suite. | sat-tester | integration, dependency | 2026-10-30T12:53:00+05:30
INT-008 | INTEGRATION | Windows service Memurai is running | environment | major | PASS | 0 | Status: Running |  |  |  | windows-service | Start-Service Memurai from an elevated PowerShell. | sat-tester | integration, service | 2026-10-30T12:53:03+05:30
INT-009 | INTEGRATION | Windows service MySQL80 is running | environment | major | PASS | 0 | Status: Running |  |  |  | windows-service | Start-Service MySQL80 from an elevated PowerShell. | sat-tester | integration, service | 2026-10-30T12:53:03+05:30
INT-010 | INTEGRATION | 2 ChatServer process(es) are running | environment | critical | PASS | 0 | Expected at least 2, found 2. |  |  |  | process-missing | Start ChatServer.exe from the project root and check its log. | sat-tester | integration, process | 2026-10-30T12:53:05+05:30
INT-011 | INTEGRATION | 1 LoadBalancer process(es) are running | environment | critical | PASS | 0 | Expected at least 1, found 1. |  |  |  | process-missing | Start LoadBalancer.exe from the project root and check its log. | sat-tester | integration, process | 2026-10-30T12:53:05+05:30
INT-012 | INTEGRATION | 1 DBWriter process(es) are running | environment | major | PASS | 0 | Expected at least 1, found 1. |  |  |  | process-missing | Start DBWriter.exe from the project root and check its log. | sat-tester | integration, process | 2026-10-30T12:53:05+05:30
INT-013 | INTEGRATION | Valid credentials authenticate through the load balancer | auth | critical | PASS | 0 | user1 -> server1; user2 -> server2 | [5 empty] | sat-tester | integration, auth | 2026-10-30T12:53:05+05:30
INT-014 | INTEGRATION | Round-robin places two users on different chat servers | load-balancing | major | PASS | 0 | serverIds: server1 and server2 |  |  |  | load-balancing | Confirm both backends are healthy and the balancer alternates sessions. | sat-tester | integration, load-balancing | 2026-10-30T12:53:05+05:30
INT-015 | INTEGRATION | Presence list includes both connected users | presence | major | PASS | 0 | Online users: user1, user2 |  |  |  | presence-list | Verify Redis presence keys and the presence_list handler. | sat-tester | integration, presence | 2026-10-30T12:53:05+05:30
INT-016 | INTEGRATION | Redis responds to PING | cache | major | PASS | 0 | PING -> PONG |  |  |  | redis-ping | Start Memurai/Redis and verify port 6379. | sat-tester | integration, redis | 2026-10-30T12:53:05+05:30
INT-017 | INTEGRATION | Redis stores the authenticated user cache/presence | cache | major | PASS | 0 | chat:online='server1'; chat:user=present |  |  |  | redis-cache | Check the auth cache write path in RedisCache. | sat-tester | integration, redis | 2026-10-30T12:53:05+05:30
INT-018 | INTEGRATION | Personal message is acknowledged and delivered across servers | messaging | critical | PASS | 1 | clientMsgId=SAT-20261030-125247-0f29d0-personal; messageId=msg-server1-1-17933449855531485; latency=1.7 ms; servers server1 -> server2 |  |  |  | personal-chat | Check Redis Pub/Sub routing and SendToUser. | auto-healer | integration, chat, cross-server | 2026-10-30T12:53:05+05:30
INT-019 | INTEGRATION | Typing indicator is forwarded to the peer | presence | major | PASS | 0 | isTyping=true | [5 empty] | sat-tester | integration, typing | 2026-10-30T12:53:05+05:30
INT-020 | INTEGRATION | Group creation returns a group id and member count | groups | critical | PASS | 0 | groupId=grp-3fb660ac3d54d0-e4a6; members=user1,user2 |  |  |  | group-create | Check tbl_Groups/tbl_GroupMembers writes. | auto-healer | integration, groups | 2026-10-30T12:53:05+05:30
INT-021 | INTEGRATION | Added member receives group_added notification | groups | major | PASS | 0 | groupName=SAT-20261030-125247-0f29d0 group | [5 empty] | sat-tester | integration, groups, presence | 2026-10-30T12:53:05+05:30
INT-022 | INTEGRATION | Group message is acknowledged and delivered to members | groups | critical | PASS | 0 | groupId=grp-3fb660ac3d54d0-e4a6; messageId=msg-server1-2-17933449855772140 |  |  |  | group-chat | Check group membership cache and Pub/Sub fan-out. | auto-healer | integration, groups, chat | 2026-10-30T12:53:05+05:30
INT-023 | INTEGRATION | Group history returns the persisted message | history | major | PASS | 0 | history count=1 |  |  |  | group-history | Verify DBWriter consumed the Kafka event. | auto-healer | integration, history, database | 2026-10-30T12:53:07+05:30
INT-024 | INTEGRATION | Personal history request completes | history | major | PASS | 0 | history count=20 | [5 empty] | sat-tester | integration, history | 2026-10-30T12:53:07+05:30
INT-025 | INTEGRATION | UDP heartbeat through the load balancer returns hb_ack | heartbeat | major | PASS | 0 | ack serverId=server1; status=online |  |  |  | heartbeat | Check UDP 5001 forwarding to 7001/7002. | auto-healer | integration, udp, heartbeat | 2026-10-30T12:53:07+05:30
INT-026 | INTEGRATION | Invalid password is rejected | auth | critical | PASS | 0 | Invalid credentials |  |  |  | auth-bypass | Verify Redis/MySQL credential validation. | auto-healer | integration, auth, security | 2026-10-30T12:53:07+05:30
INT-027 | INTEGRATION | Empty message is rejected with an error frame | validation | major | PASS | 0 | Message text is empty |  |  |  | validation | Check the message validation branch. | auto-healer | integration, validation | 2026-10-30T12:53:07+05:30
INT-028 | INTEGRATION | Over-8000-character message is rejected | validation | major | PASS | 0 | Message is too long (maximum 8000 characters) |  |  |  | validation | Check kMaxMessageLength enforcement. | auto-healer | integration, validation | 2026-10-30T12:53:07+05:30
INT-029 | INTEGRATION | Unknown recipient is rejected | validation | major | PASS | 0 | Recipient not found |  |  |  | validation | Check recipient lookup. | auto-healer | integration, validation | 2026-10-30T12:53:07+05:30
INT-030 | INTEGRATION | SQL-injection-shaped user id is rejected | security | critical | PASS | 0 | Recipient not found |  |  |  | injection | Keep parameterised SQL and user-id validation. | auto-healer | integration, security | 2026-10-30T12:53:07+05:30
INT-031 | INTEGRATION | Message throughput and latency stay within thresholds | performance | major | PASS | 146 | 40 messages; avg=3.7 ms; p95=5.0 ms; thresholds avg<=250 ms, p95<=750 ms. |  |  |  | latency | Investigate Redis/Kafka/DBWriter backpressure. | sat-tester | integration, performance | 2026-10-30T12:53:07+05:30
INT-032 | INTEGRATION | Every stress message was acknowledged | reliability | critical | PASS | 0 | 40/40 acks contained a messageId. |  |  |  | message-loss | Check server send failures and Redis routing. | auto-healer | integration, reliability | 2026-10-30T12:53:07+05:30
INT-033 | INTEGRATION | Kafka topic chat-messages exists and has partitions | messaging | major | PASS | 0 | Topic: chat-messages TopicId: 8RRYMVy4TlOgxd6IhjtX4g PartitionCount: 1 ReplicationFactor: 1 Configs: min.insync.replicas=1,segment.bytes=1073741824 Topic: chat-messages Partition: 0 Leader: 1 Replicas: 1 Isr: 1 Elr: LastKnownElr: 2026-10-30T07:23:09.104405900Z main ERROR Reconfiguration failed: No configuration found for '14dad5dc' at 'null' in 'null' |  |  |  | kafka-topic | Create chat-messages and restart the services. | sat-tester | integration, kafka | 2026-10-30T12:53:10+05:30
INT-034 | INTEGRATION | Personal message is persisted by DBWriter | persistence | critical | PASS | 0 | MessageId=msg-server1-1-17933449855531485; UserId=user1; type=personal; target=user2 |  |  |  | persistence | Check Kafka, DBWriter and MySQL ODBC connectivity. | auto-healer | integration, database, kafka, dbwriter | 2026-10-30T12:53:11+05:30
INT-035 | INTEGRATION | Group message is persisted by DBWriter | persistence | critical | PASS | 0 | MessageId=msg-server1-2-17933449855772140; UserId=user1; type=group; target=grp-3fb660ac3d54d0-e4a6 |  |  |  | persistence | Check Kafka, DBWriter and MySQL ODBC connectivity. | auto-healer | integration, database, kafka, dbwriter | 2026-10-30T12:53:11+05:30
INT-036 | INTEGRATION | Logout returns a bye frame | session | major | PASS | 0 | bye received. |  |  |  | logout | Check the logout branch and connection cleanup. | auto-healer | integration, session | 2026-10-30T12:53:11+05:30
INT-037 | INTEGRATION | Client can reconnect and re-authenticate after logout | session | critical | PASS | 0 | A new session authenticated successfully. | [5 empty] | sat-tester | integration, session, reconnect | 2026-10-30T12:53:11+05:30
INT-038 | INTEGRATION | ChatClient.exe launches and creates a window | ui | major | PASS | 0 | Window title: DualThread - Sign in |  |  |  | ui-launch | Run the client on an interactive desktop and inspect logs\client.log. | sat-tester | integration, ui | 2026-10-30T12:53:13+05:30
INT-039 | INTEGRATION | No fatal runtime errors were written during the suite | runtime | critical | PASS | 0 | No fatal errors. |  |  |  | runtime-fatal | Inspect the service log and fix the crash before release. | auto-healer | integration, logs | 2026-10-30T12:53:14+05:30
INT-040 | INTEGRATION | No unexpected ERROR lines were written during the suite | runtime | major | PASS | 0 | No ERROR lines. |  |  |  | runtime-error | Inspect the referenced service log and classify or fix the error. | sat-tester | integration, logs | 2026-10-30T12:53:14+05:30
ACC-001 | ACCEPTANCE | REQ-01 Personal messaging across two servers | acceptance | major | PASS | 0 | Source evidence: ChatServer/TcpServer.cpp, ChatClient/ChatSession.cpp; runtime evidence: INT-018, INT-022 |  |  |  | requirement-evidence | Restore the implementation or add runtime coverage for this requirement. | auto-healer | acceptance, REQ-01 | 2026-10-30T12:53:14+05:30
ACC-002 | ACCEPTANCE | REQ-02 Group creation, membership and group messaging | acceptance | major | PASS | 0 | Source evidence: ChatServer/TcpServer.cpp, ChatServer/TcpServer.cpp, database/schema.sql; runtime evidence: INT-020, INT-021, INT-022 |  |  |  | requirement-evidence | Restore the implementation or add runtime coverage for this requirement. | auto-healer | acceptance, REQ-02 | 2026-10-30T12:53:14+05:30
ACC-003 | ACCEPTANCE | REQ-03 Online/offline presence | acceptance | major | PASS | 0 | Source evidence: ChatServer/TcpServer.cpp, ChatClient/MainDlg.cpp; runtime evidence: INT-015, INT-021 |  |  |  | requirement-evidence | Restore the implementation or add runtime coverage for this requirement. | auto-healer | acceptance, REQ-03 | 2026-10-30T12:53:14+05:30
ACC-004 | ACCEPTANCE | REQ-04 Typing indicator | acceptance | major | PASS | 0 | Source evidence: ChatServer/TcpServer.cpp, ChatClient/MainDlg.cpp; runtime evidence: INT-019 |  |  |  | requirement-evidence | Restore the implementation or add runtime coverage for this requirement. | auto-healer | acceptance, REQ-04 | 2026-10-30T12:53:14+05:30
ACC-005 | ACCEPTANCE | REQ-05 Unread badges with previews | acceptance | major | PASS | 0 | Source evidence: ChatClient/MainDlg.cpp, ChatClient/UiControls.cpp; runtime evidence: INT-038 |  |  |  | requirement-evidence | Restore the implementation or add runtime coverage for this requirement. | auto-healer | acceptance, REQ-05 | 2026-10-30T12:53:14+05:30
ACC-006 | ACCEPTANCE | REQ-06 Server-side history (last 100 messages) | acceptance | major | PASS | 0 | Source evidence: ChatServer/TcpServer.cpp, ChatServer/MySQLDatabase.cpp; runtime evidence: INT-023, INT-024 |  |  |  | requirement-evidence | Restore the implementation or add runtime coverage for this requirement. | auto-healer | acceptance, REQ-06 | 2026-10-30T12:53:14+05:30
ACC-007 | ACCEPTANCE | REQ-07 Automatic reconnection with backoff | acceptance | major | PASS | 0 | Source evidence: ChatClient/ChatSession.cpp, ChatClient/MainDlg.cpp; runtime evidence: INT-037 |  |  |  | requirement-evidence | Restore the implementation or add runtime coverage for this requirement. | auto-healer | acceptance, REQ-07 | 2026-10-30T12:53:14+05:30
ACC-008 | ACCEPTANCE | REQ-08 UDP heartbeat and RTT monitoring | acceptance | major | PASS | 0 | Source evidence: ChatServer/UdpHeartbeat.cpp, LoadBalancer/LoadBalancer.cpp; runtime evidence: INT-025 |  |  |  | requirement-evidence | Restore the implementation or add runtime coverage for this requirement. | auto-healer | acceptance, REQ-08 | 2026-10-30T12:53:14+05:30
ACC-009 | ACCEPTANCE | REQ-09 Redis auth cache, presence and Pub/Sub routing | acceptance | major | PASS | 0 | Source evidence: ChatServer/TcpServer.cpp, ChatServer/RedisCache.cpp; runtime evidence: INT-016, INT-017, INT-018 |  |  |  | requirement-evidence | Restore the implementation or add runtime coverage for this requirement. | auto-healer | acceptance, REQ-09 | 2026-10-30T12:53:14+05:30
ACC-010 | ACCEPTANCE | REQ-10 Kafka event pipeline | acceptance | major | PASS | 0 | Source evidence: ChatServer/KafkaProducer.cpp, DBWriter/KafkaConsumer.cpp; runtime evidence: INT-033, INT-034, INT-035 |  |  |  | requirement-evidence | Restore the implementation or add runtime coverage for this requirement. | auto-healer | acceptance, REQ-10 | 2026-10-30T12:53:14+05:30
ACC-011 | ACCEPTANCE | REQ-11 MySQL persistence through DBWriter | acceptance | major | PASS | 0 | Source evidence: DBWriter/DatabaseWriter.cpp, database/schema.sql; runtime evidence: STR-023, STR-024, INT-023, INT-034, INT-035 |  |  |  | requirement-evidence | Restore the implementation or add runtime coverage for this requirement. | auto-healer | acceptance, REQ-11 | 2026-10-30T12:53:14+05:30
ACC-012 | ACCEPTANCE | REQ-12 Round-robin load balancing and health checks | acceptance | major | PASS | 0 | Source evidence: LoadBalancer/BackendManager.cpp, LoadBalancer/BackendManager.cpp; runtime evidence: INT-014 |  |  |  | requirement-evidence | Restore the implementation or add runtime coverage for this requirement. | auto-healer | acceptance, REQ-12 | 2026-10-30T12:53:14+05:30
ACC-013 | ACCEPTANCE | REQ-13 Native MFC desktop UI | acceptance | major | PASS | 0 | Source evidence: ChatClient/ChatClient.cpp, ChatClient/ChatClient.vcxproj; runtime evidence: INT-038 |  |  |  | requirement-evidence | Restore the implementation or add runtime coverage for this requirement. | auto-healer | acceptance, REQ-13 | 2026-10-30T12:53:14+05:30
ACC-014 | ACCEPTANCE | REQ-14 Input validation and injection resistance | acceptance | major | PASS | 0 | Source evidence: ChatServer/TcpServer.cpp, ChatServer/MySQLDatabase.cpp; runtime evidence: INT-026, INT-027, INT-028, INT-029, INT-030 |  |  |  | requirement-evidence | Restore the implementation or add runtime coverage for this requirement. | auto-healer | acceptance, REQ-14 | 2026-10-30T12:53:14+05:30
ACC-015 | ACCEPTANCE | REQ-15 Reproducible Release¦x64 build and deployment | acceptance | major | PASS | 0 | Source evidence: CppChatMessaging.sln, scripts/start-all.ps1; runtime evidence: ENV-004, ENV-005, BLD-001, BLD-002, BLD-003, BLD-004, BLD-005, BLD-006 |  |  |  | requirement-evidence | Restore the implementation or add runtime coverage for this requirement. | auto-healer | acceptance, REQ-15 | 2026-10-30T12:53:14+05:30
ACC-016 | ACCEPTANCE | Documented UI evidence screenshots are present | documentation | minor | PASS | 0 | 8 screenshots found in docs/screenshots. |  |  |  | documentation-evidence | Capture the missing UI states. | sat-tester | acceptance, docs, ui | 2026-10-30T12:53:14+05:30
ACC-017 | ACCEPTANCE | Test-results and traceability documents exist | documentation | minor | PASS | 0 | TEST_RESULTS=present; TRACEABILITY=present. |  |  |  | documentation-evidence | Generate the documents from this SAT report. | sat-tester | acceptance, docs | 2026-10-30T12:53:14+05:30
RPT-001 | REPORT | Excel acceptance workbook was generated | reporting | critical | PASS | 0 | The workbook is generated after all test phases complete. | reports/SAT_Report_20261030-125141.xlsx |  |  |  |  | sat-tester | report, excel | 2026-10-30T12:53:14+05:30

## Defects
Defect Queue
Failures and warnings for the release engineer and auto-healer agents.
Test ID | Status | Severity | Phase | Test | Error Type | File | Line | Details | Remediation | Owner
STA-006 | WARN | major | STATIC ANALYSIS | No plaintext production credentials in source or configuration | plaintext-secret |  | 0 | Demo credentials are present (expected for this assessment build): config/dbwriter.ini: value=T*******% config/server1.ini: value=T*******% config/server2.ini: value=T*******% | Move credentials to environment variables or a secret store before production use. | sat-tester
ENV-011 | WARN | minor | ENVIRONMENT | Working tree is clean before testing | dirty-tree |  | 0 | Uncommitted changes are present; the report describes the working tree, not a tagged commit. | Commit or stash changes before a release run. | sat-tester

## File Inventory
File Inventory
All 120 tracked project files were read, hashed and validated.
Path | Category | Bytes | Lines | SHA-256 | Encoding | Status | Notes | Modified
.gitignore | repository | 546 | 58 | ac80c9cda9e42563bdf6466a70df84da6f39d9493e38267cf89bdffccce536c0 | utf-8-sig | PASS |  | 2026-10-30T12:04:44+05:30
.opencode/agents/auto-healer.md | agent-definition | 6312 | 166 | 3dec78a47b9f214c29f1cf48596e7ebeb630f3e91a3ae4d49b3cf0cf7305bd20 | utf-8-sig | PASS |  | 2026-10-30T12:01:57+05:30
.opencode/agents/release-engineer.md | agent-definition | 3804 | 120 | 3f121ce1b175e0e4fb49204b285ae59ac94cce1af847ad41cf172e07c0b68b4f | utf-8-sig | PASS |  | 2026-10-30T12:01:34+05:30
.opencode/agents/sat-tester.md | agent-definition | 4991 | 112 | fe4b79f70cfe295c0b4aa5a3c9bd934a695220e49a7c1ef7466994cabb2028c4 | utf-8-sig | PASS |  | 2026-10-30T12:01:22+05:30
AGENTS.md | other | 1337 | 33 | e01b4766151df289c0025718930c0e319ec6703160c8f3be5b466df49e7a087e | utf-8-sig | PASS |  | 2026-10-30T12:14:22+05:30
bin/Debug/ChatClient.exe | build-artifact | 1209344 | 0 | 7485d84e9077f1958c7e3a1422c244d78ec3b4c372db69542cc08510b36145ec | binary | PASS | PE x64 | 2026-10-22T16:43:36+05:30
bin/Release/ChatClient.exe | build-artifact | 715776 | 0 | 903813fbd33844a50c5b88cc8f1aaa3849d0c7c2819eb2657811a0f87b27ac6d | binary | PASS | PE x64 | 2026-10-30T12:33:44+05:30
bin/Release/ChatServer.exe | build-artifact | 672256 | 0 | 9ebc6ec7e9ac80f13808c92e56f4016757abc3cabbd642b63599a43e995178e3 | binary | PASS | PE x64 | 2026-10-30T12:33:38+05:30
bin/Release/DBWriter.exe | build-artifact | 464896 | 0 | 846338834ca1106348c53c0a5d4ee9ce09515a220d092164fe46130fa9b29842 | binary | PASS | PE x64 | 2026-10-30T12:33:20+05:30
bin/Release/hiredis.dll | build-artifact | 120832 | 0 | 2026682b3031cc63f90d4a6ab45962370587f34288d3f94d3db61024b7c358f4 | binary | PASS | PE x64 | 2026-10-21T18:28:59+05:30
bin/Release/LoadBalancer.exe | build-artifact | 483840 | 0 | 531797ed12cd3b15041ef68214010ff45a97ac017a2fb06734ef82fb6a779265 | binary | PASS | PE x64 | 2026-10-30T12:33:22+05:30
bin/Release/lz4.dll | build-artifact | 130048 | 0 | d029d2e9cb7ca8433e3f5d1a0717d3f026d79054956612cd7fdf4052d2d99738 | binary | PASS | PE x64 | 2026-10-07T22:35:01+05:30
bin/Release/rdkafka.dll | build-artifact | 2398208 | 0 | 6ba3e8ca451449949837fa3861a3646f18e6fffd6961992a79a0331de3d65e30 | binary | PASS | PE x64 | 2026-10-07T22:36:23+05:30
build-release.log | other | 29917 | 301 | b4191713b3be4ffec6358b7f747eb43a338e450c442e2d6eb83182973d1ebab6 | utf-8-sig | PASS |  | 2026-10-22T14:30:50+05:30
ChatClient/ChatClient.cpp | client-source | 1858 | 66 | e46a3aecbeddde37166988840dd953821ee00577f415cf8d45f1b5563ff0cef1 | utf-8-sig | PASS |  | 2026-10-22T00:32:14+05:30
ChatClient/ChatClient.h | client-source | 945 | 42 | 7f3f0e69c11e5b53e013c54d80b283bd3b7376fd9295a1072632cd3f4648e5e7 | utf-8-sig | PASS |  | 2026-10-22T00:20:52+05:30
ChatClient/ChatClient.rc | client-source | 696 | 28 | fc1c73fc81700ec0260ba4f6bbbb3ff13216b95c2faaf3af6bfd37408d05606b | utf-8-sig | PASS |  | 2026-10-22T00:21:26+05:30
ChatClient/ChatClient.vcxproj | client-source | 5638 | 129 | 873f55262102fdda9ab22a3dd47c4f19af42720fe48b4405e45dd814ea7d4ee2 | utf-8-sig | PASS |  | 2026-10-22T00:31:12+05:30
ChatClient/ChatClient.vcxproj.user | client-source | 168 | 0 | c06a75b13f855a94d46616796e024c52b499f8f92cf00ccb571ddbc6ff574676 | binary | PASS | opaque binary tracked as artifact | 2026-10-22T16:40:00+05:30
ChatClient/ChatSession.cpp | client-source | 14117 | 435 | 460b9d22ce496e3fdfad12311ebf3898ea940656282b46c0b5f27e5991ca1385 | utf-8-sig | PASS |  | 2026-10-22T00:25:42+05:30
ChatClient/ChatSession.h | client-source | 2439 | 80 | 1ba626fb459d952bb41d756446a4fd0e64954e80d1374cbba868be99a1a4bccc | utf-8-sig | PASS |  | 2026-10-22T00:19:32+05:30
ChatClient/GroupDlg.cpp | client-source | 9571 | 256 | 79348e83bb51ca9031f3dce5a532b09364ecb0e36d428b6487f6b776fd30dd0b | utf-8-sig | PASS |  | 2026-10-22T00:32:50+05:30
ChatClient/GroupDlg.h | client-source | 1382 | 60 | a6217216b9669978945be3cc3b4a5be672cad99700b04bbb9349802850c54b30 | utf-8-sig | PASS |  | 2026-10-22T00:32:20+05:30
ChatClient/LoginDlg.cpp | client-source | 16180 | 456 | e73a8c1d6680d66e12d94dbd0423f0a292e9e35265d060c3bc86446647cf413d | utf-8-sig | PASS |  | 2026-10-22T00:32:14+05:30
ChatClient/LoginDlg.h | client-source | 1711 | 73 | f568bffc49ea2c22e3fba6ea4417f5d674c541714cd8327484de92d5b666ba36 | utf-8-sig | PASS |  | 2026-10-22T00:32:14+05:30
ChatClient/MainDlg.cpp | client-source | 39484 | 1114 | 575b3b1cfc6556945c70bca6e29639daf5b8abf8254f607956ed41062b80479d | utf-8-sig | PASS |  | 2026-10-22T08:33:28+05:30
ChatClient/MainDlg.h | client-source | 4136 | 119 | e24bbfb699975ffb3a97fc96fa992c94134ea4628097702ffcc36a422ea53e37 | utf-8-sig | PASS |  | 2026-10-22T00:32:14+05:30
ChatClient/resource.h | client-source | 1422 | 45 | 4ba4a191a18c207dbc0bbead69c865b693a5f32e142bcbc7bed8170b020a5830 | utf-8-sig | PASS |  | 2026-10-22T00:21:10+05:30
ChatClient/UiControls.cpp | client-source | 27162 | 805 | aef19031758983ec0a666030bfbd1b04fdf382eeb3b3193fc1f27c064a53c40f | utf-8-sig | PASS |  | 2026-10-22T00:32:14+05:30
ChatClient/UiControls.h | client-source | 4768 | 168 | ae285ad890e1c48c1bcb31fa5b2b4b6927abba06c94a76b1b642235eb096711d | utf-8-sig | PASS |  | 2026-10-22T00:22:56+05:30
ChatClient/UiTheme.h | client-source | 7590 | 188 | 1b238298e2d2da69487626a5a5758ad1d50ccd9d9596df184136df5f4858b7db | utf-8-sig | PASS |  | 2026-10-22T00:21:46+05:30
ChatServer/ChatServer.vcxproj | server-source | 4915 | 108 | f5a1907dc9b944640098bb4b9856a42bf96d6b491596925b9968c447da75a6ce | utf-8-sig | PASS |  | 2026-10-22T00:12:40+05:30
ChatServer/ChatServer.vcxproj.user | server-source | 168 | 0 | c06a75b13f855a94d46616796e024c52b499f8f92cf00ccb571ddbc6ff574676 | binary | PASS | opaque binary tracked as artifact | 2026-10-22T16:40:00+05:30
ChatServer/KafkaProducer.cpp | server-source | 3951 | 120 | 1b9675380f4e5cf23d2622b251dc03e096f4481c749add6bd45f2b1ebc9e5d63 | utf-8-sig | PASS |  | 2026-10-22T00:04:46+05:30
ChatServer/KafkaProducer.h | server-source | 846 | 32 | aa87585b3c78748966c89a5dcdae243780f36c21dc715cfc7cf0b841ebc189ef | utf-8-sig | PASS |  | 2026-10-22T00:04:46+05:30
ChatServer/main.cpp | server-source | 3235 | 108 | 2bd0fa60e3f864837da4b0a7dcc569dab658ad7f64e824b5a61e8fb3399ff1eb | utf-8-sig | PASS |  | 2026-10-22T16:36:18+05:30
ChatServer/MySQLDatabase.cpp | server-source | 20743 | 541 | 59079d98b55c0f5300e383c2d02b7a573a22c922e363e197db3ed8b91b13b503 | utf-8-sig | PASS |  | 2026-10-22T00:40:24+05:30
ChatServer/MySQLDatabase.h | server-source | 2016 | 66 | 9f4c30820b7c8cd9f217d28e3dbefb500c0a5502ee1003d42ae898c93d389fe3 | utf-8-sig | PASS |  | 2026-10-22T00:07:20+05:30
ChatServer/RedisCache.cpp | server-source | 11149 | 300 | 43e79c4cf810cefe1b460d14da8ba630eceb3400b316ce9cfb2747e9387b1306 | utf-8-sig | PASS |  | 2026-10-30T12:22:01+05:30
ChatServer/RedisCache.h | server-source | 2151 | 61 | 42f180eb1928f9f84d72f2edf508d5650bb87a20fa72d1c089b3b161be4ce0a3 | utf-8-sig | PASS |  | 2026-10-30T12:21:44+05:30
ChatServer/ServerConfig.cpp | server-source | 3403 | 74 | 3dfaa12762d28a474510c1f4c40bbfaa12fe6baac8bfdb7b449810541fd8dff8 | utf-8-sig | PASS |  | 2026-10-22T00:02:38+05:30
ChatServer/ServerConfig.h | server-source | 1019 | 34 | 6a0d8bef8e79c198ff6b8fdd0bf17edbca68ee26b94919664e32188315200ee1 | utf-8-sig | PASS |  | 2026-10-22T00:02:38+05:30
ChatServer/TcpServer.cpp | server-source | 34852 | 1002 | fcb95a80e6ac607daf505e2862d48871f9bdf4ef507a2e5ca794ccc236bcb090 | utf-8-sig | PASS |  | 2026-10-22T16:38:40+05:30
ChatServer/TcpServer.h | server-source | 3719 | 105 | 565068d6f10cfefc1b8f6f97efe9658d907c757397aa269456ac5d3b723569a5 | utf-8-sig | PASS |  | 2026-10-22T00:06:14+05:30
ChatServer/UdpHeartbeat.cpp | server-source | 4629 | 135 | b3a6d2ee0c5be5090e77a7cb11c606032ad9f4f8ced84287d0d084539cc1f0de | utf-8-sig | PASS |  | 2026-10-22T00:03:52+05:30
ChatServer/UdpHeartbeat.h | server-source | 1099 | 39 | 2acaa3113204a115f81ae1be6b1fd62e91a64c8d10540776e84b9c1219e651db | utf-8-sig | PASS |  | 2026-10-22T00:03:52+05:30
Common/Ini.cpp | shared-source | 2701 | 72 | 32055f9955f20e7c6e6a48ad5ea2c983e6b1ddd44ae9178897f336ec417d8419 | utf-8-sig | PASS |  | 2026-10-22T00:02:04+05:30
Common/Ini.h | shared-source | 542 | 13 | 102eed87ffab045cb6e80f21071ea5bbe325b5248c284499a532c5ecec4c1c8c | utf-8-sig | PASS |  | 2026-10-22T00:02:04+05:30
Common/JsonUtil.cpp | shared-source | 6819 | 210 | 8eb2cc4434a0b2669574b8c0052721cee2d1544db604270b64b754f3c247b1e6 | utf-8-sig | PASS |  | 2026-10-22T00:02:18+05:30
Common/JsonUtil.h | shared-source | 729 | 17 | 7beb0cc28b4889944fe94f387ab97312f7a9bbe7043daeb8685fc9673e54bfcd | utf-8-sig | PASS |  | 2026-10-22T00:02:18+05:30
Common/Logger.cpp | shared-source | 1179 | 48 | 5ce240724be5a14cf87a7d9b487cde52f176c919596a405f347bcc4a5e588431 | utf-8-sig | PASS |  | 2026-10-21T18:20:06+05:30
Common/Logger.h | shared-source | 270 | 12 | bec89686b51cfd55f52c66906ff5714585105f399d7013d4475b17f48cc37ff7 | utf-8-sig | PASS |  | 2026-10-21T18:20:06+05:30
Common/Protocol.cpp | shared-source | 2621 | 80 | 27b3a318d3218c23bfb7a7d5992ddfcd673ac5219d57e0df8fb443297b25b34b | utf-8-sig | PASS |  | 2026-10-21T18:20:06+05:30
Common/Protocol.h | shared-source | 453 | 17 | 6c2a5c4ab59c584b43ad6238313ecb05645ab935f466db2235044fe49e70f7a9 | utf-8-sig | PASS |  | 2026-10-21T18:20:06+05:30
Common/Sha256.cpp | shared-source | 3173 | 66 | c1d8ee9507353f09debe8515ba0384bb1f4bc9c3636d491dabe4172513dc0f50 | utf-8-sig | PASS |  | 2026-10-30T12:22:03+05:30
Common/Sha256.h | shared-source | 82 | 5 | b1cad31a852774993a147154e3aa2d1f8bda5f0d7dead10bd898578131128440 | utf-8-sig | PASS |  | 2026-10-21T18:20:06+05:30
Common/ThreadSafeQueue.h | shared-source | 1748 | 68 | 8db61eace1ef1f92b7edad9282d5417db8d4dcf8f2d7923038da7593ef9ebcae | utf-8-sig | PASS |  | 2026-10-22T00:02:04+05:30
config/client.ini | configuration | 109 | 6 | b862ef3e3968355fa9bcbe81a86a70ac38ee962bcdf59088eedeba2f836a4e3b | utf-8-sig | PASS |  | 2026-10-22T00:12:20+05:30
config/dbwriter.ini | configuration | 263 | 11 | 67a765bb23a64b66eee1d446e28afad1d6734397317e7cc79a82797506cdc20c | utf-8-sig | PASS |  | 2026-10-22T00:12:20+05:30
config/loadbalancer.ini | configuration | 255 | 18 | c711a21238d0fc5dd413f05a5beebf060a0311211d751f6785b1034b7717f9ac | utf-8-sig | PASS |  | 2026-10-21T18:20:06+05:30
config/server1.ini | configuration | 438 | 29 | 2f6a1a119a413b974a54fc37f20f822d62ca5d02d733556b0262f5499f60ec25 | utf-8-sig | PASS |  | 2026-10-22T00:12:20+05:30
config/server2.ini | configuration | 438 | 29 | 7c3b6f867a06a718798f31dcd7e045f13c956e1a3dea57622106431f29faf38e | utf-8-sig | PASS |  | 2026-10-22T00:12:20+05:30
CppChatMessaging.sln | build-system | 2323 | 39 | 4866100e788931e3180d308ad8b3d3cef999ff9eaf2e3afb2121ce18c16b9e12 | utf-8-sig | PASS |  | 2026-10-22T16:40:22+05:30
database/migration_v2_groups.sql | database | 2009 | 55 | 75867effe520acabb2264288a16f5302cc581a1a9653a22ee4879030cae6d73f | utf-8-sig | PASS |  | 2026-10-22T00:11:16+05:30
database/sample_data.sql | database | 468 | 13 | 96907d0ea4aa9d7b5e0b1979ef70ecf973321214d3cf909d6b6f8bcea1137811 | utf-8-sig | PASS |  | 2026-10-21T18:20:06+05:30
database/schema.sql | database | 1399 | 42 | e6600f5ad6a56f903a7588bfbfc47becba656ac1ebb08dd04ed07b828b45801d | utf-8-sig | PASS |  | 2026-10-22T00:11:16+05:30
DBWriter/DatabaseWriter.cpp | dbwriter-source | 10566 | 293 | 41809810f8840c9662d2068ca4d1a568031c6e1b34b6709b16e2434ba4ba4ffc | utf-8-sig | PASS |  | 2026-10-22T00:13:36+05:30
DBWriter/DatabaseWriter.h | dbwriter-source | 1412 | 41 | c1d8244b85636234e35000f93c3fe0c87f823e8d7d10812999f016ceab7aeed8 | utf-8-sig | PASS |  | 2026-10-22T00:08:18+05:30
DBWriter/DBWriter.vcxproj | dbwriter-source | 4467 | 86 | d485f79d96a5ea7df7b152c8bed121c3ae54d8b2dca1cd048124170e354bdb6a | utf-8-sig | PASS |  | 2026-10-21T19:12:28+05:30
DBWriter/DBWriter.vcxproj.user | dbwriter-source | 168 | 0 | c06a75b13f855a94d46616796e024c52b499f8f92cf00ccb571ddbc6ff574676 | binary | PASS | opaque binary tracked as artifact | 2026-10-22T16:40:00+05:30
DBWriter/KafkaConsumer.cpp | dbwriter-source | 4288 | 127 | a176645f70867036eb650ad7ee960b6397480f109ae1ee64cf9d79bc45cbe5b0 | utf-8-sig | PASS |  | 2026-10-22T00:08:48+05:30
DBWriter/KafkaConsumer.h | dbwriter-source | 929 | 37 | 41e65a976e43b24eb72377b3d3af6b342ee72ee4e610ac1d5a147dc8311292d6 | utf-8-sig | PASS |  | 2026-10-22T00:08:34+05:30
DBWriter/main.cpp | dbwriter-source | 3498 | 92 | 013380fc193fb5762a793aa9b77f8e740fcbd146f8432956715c5e7736df52fa | utf-8-sig | PASS |  | 2026-10-22T08:35:32+05:30
docs/AGENTS.md | documentation | 12521 | 296 | 186558120f5fa5b4ea09d86751961759d77e6259ff19cb6cdfe9b2e957350fe5 | utf-8-sig | PASS |  | 2026-10-30T12:14:05+05:30
docs/ARCHITECTURE.md | documentation | 17155 | 359 | a63c1693008ac14c1376857b969091348c05ceff1c0d392615da2f8226ddf230 | utf-8-sig | PASS |  | 2026-10-22T10:04:08+05:30
docs/DualThread-Execution-Guide.pdf | documentation | 696957 | 0 | 254bc8eb823d256fe888415e6c13b0338c0d92bf568bd300bafd046c0a4b2c1c | binary | PASS |  | 2026-10-22T10:39:26+05:30
docs/screenshots/group-chat.png | documentation | 48963 | 0 | f67a8513ba7af0ec82d0a46482819c90c6464baf46170d0f6847a4eb1d4be303 | binary | PASS |  | 2026-10-22T08:59:34+05:30
docs/screenshots/group-joined.png | documentation | 40086 | 0 | 632bfd817d3a6e792520241952aa0ef1d4859d2a61545d8719e58842c257e900 | binary | PASS |  | 2026-10-22T09:01:24+05:30
docs/screenshots/login.png | documentation | 34217 | 0 | 2ed2d7d068c91971ef1ddc3578d0677180033289d75234f41234f0bdd5537e71 | binary | PASS |  | 2026-10-22T09:02:50+05:30
docs/screenshots/personal-chat.png | documentation | 62017 | 0 | 8d5eda3efb028810c15fc6152882599cdd14ab90afabf2c0c6087963fea1d38e | binary | PASS |  | 2026-10-22T09:00:12+05:30
docs/screenshots/reconnect-feedback.png | documentation | 49791 | 0 | 33a94a133ee2180b8a53fc257e5761b573c922236c9a809c8698446d2c6e0759 | binary | PASS |  | 2026-10-22T09:01:24+05:30
docs/screenshots/reconnected.png | documentation | 50436 | 0 | 9b38154fb49732a4eceda9edf9dba8418c8b9799f961c1a50dabe97306ec6513 | binary | PASS |  | 2026-10-22T09:01:24+05:30
docs/screenshots/typing-indicator.png | documentation | 61563 | 0 | 1f6478fd07b9d018bb11b4ad2b4f9359fef08c364650c9fbc86429d7557e99a8 | binary | PASS |  | 2026-10-22T09:00:50+05:30
docs/screenshots/unread-badge.png | documentation | 35865 | 0 | 363a130bb3143a16268fed8277c41005bd912b929d01f3e6cb7af78674572aca | binary | PASS |  | 2026-10-22T09:01:24+05:30
docs/TEST_RESULTS.md | documentation | 10938 | 197 | 488f7ba5c5cc9d8be1cb70423c05b31177f2c446f9e182f2a2f6c55b5888cc26 | utf-8-sig | PASS |  | 2026-10-22T10:04:16+05:30
docs/TRACEABILITY.md | documentation | 8360 | 76 | 5e86a057a5eb2e62ed16830134a0a572b72a6208af5d71bc0b53cb8cd8349a56 | utf-8-sig | PASS |  | 2026-10-22T10:04:18+05:30
LoadBalancer/BackendManager.cpp | loadbalancer-source | 6431 | 245 | e90606455c48e736c2c83f9be7ffa27d6a487fcd09ef80826b001f39d2c22e9e | utf-8-sig | PASS |  | 2026-10-22T14:24:40+05:30
LoadBalancer/BackendManager.h | loadbalancer-source | 944 | 40 | 31a0bc5989ea8ae4296417618a2da978abdfc219f9c6812d1ae8cbbb3e9266c5 | utf-8-sig | PASS |  | 2026-10-21T18:20:06+05:30
LoadBalancer/LoadBalancer.cpp | loadbalancer-source | 18019 | 722 | 926cc3c5535fdd1bbf20a9ebb20aaf81681820f966c7ee75457b59bef876216f | utf-8-sig | PASS |  | 2026-10-22T12:38:46+05:30
LoadBalancer/LoadBalancer.h | loadbalancer-source | 1007 | 45 | 87f216e025b1494cb3b20df1f709e5e61b57f054551cf1314e8fe5c1686b03af | utf-8-sig | PASS |  | 2026-10-22T00:10:42+05:30
LoadBalancer/LoadBalancer.vcxproj | loadbalancer-source | 4443 | 100 | a841aac541bed660cf29fc43214aeb1c37ca0a8bedb3fd49a808f7a8189ea3f6 | utf-8-sig | PASS |  | 2026-10-21T18:54:40+05:30
LoadBalancer/LoadBalancer.vcxproj.user | loadbalancer-source | 168 | 0 | c06a75b13f855a94d46616796e024c52b499f8f92cf00ccb571ddbc6ff574676 | binary | PASS | opaque binary tracked as artifact | 2026-10-22T16:40:00+05:30
LoadBalancer/main.cpp | loadbalancer-source | 956 | 39 | 2cb708ae627a56237d93980c67ac3c5c568680ceed5a11f28917c91198bd576c | utf-8-sig | PASS |  | 2026-10-22T08:36:00+05:30
LoadBalancer/TcpProxy.cpp | loadbalancer-source | 2457 | 75 | 788aaf8245c39f3a75265a09cd203d4a9f8f6ca32f141be42570201456e9e349 | utf-8-sig | PASS |  | 2026-10-22T00:09:46+05:30
LoadBalancer/TcpProxy.h | loadbalancer-source | 549 | 29 | 5343dfe21f484fd3593f55274234e491e52531dffe6bcc8f9923390c29fdd4af | utf-8-sig | PASS |  | 2026-10-22T00:09:28+05:30
README.md | repository | 21428 | 422 | 331d143e883f37b250c9d82a31a5a61dc4665f7392b94ea85f55dbd2af06df1c | utf-8-sig | PASS |  | 2026-10-30T12:14:13+05:30
run-heal.ps1 | other | 783 | 28 | c1153c882f574d535d459816331c9ca51743da248db8043dbeda1e237f23a8e4 | utf-8-sig | PASS |  | 2026-10-30T12:00:35+05:30
run-pipeline.ps1 | other | 1189 | 38 | d00fe17ee66b1ca6a27ff0ac26e15079d084ccbcac746a29a8e7bfe01d11bae4 | utf-8-sig | PASS |  | 2026-10-30T12:00:44+05:30
run-release.ps1 | other | 838 | 29 | a2efab4ed3a1d8fc3d1a9bbe6b0fb1396a427c3e68983d133e382a41d195a0a9 | utf-8-sig | PASS |  | 2026-10-30T12:00:21+05:30
run-sat.ps1 | other | 949 | 31 | 499d43b7fcd26bf322a31e87a8fec4c7558396904057921c11a3301e14e3d69f | utf-8-sig | PASS |  | 2026-10-30T12:00:18+05:30
scripts/start-all.ps1 | automation | 6903 | 176 | 0bda575783efe88f2a0474a23f9c46e1bfd05b6249e70121c914ffb9265d8baf | utf-8-sig | PASS |  | 2026-10-22T09:58:06+05:30
scripts/stop-all.ps1 | automation | 1860 | 58 | 9094d62cb68790cd458368609353f0d4a33c7ee6c3fa551a978827be6a529080 | utf-8-sig | PASS |  | 2026-10-22T09:58:06+05:30
tools/__init__.py | test-tooling | 35 | 1 | 2af127e322ae48dd806048cdd22f2ce3333b4025079ed6dc4b881a7d775aaf33 | utf-8-sig | PASS |  | 2026-10-30T12:00:00+05:30
tools/sat/__init__.py | test-tooling | 53 | 1 | 30cb404e7dbe4fbd9536231613462d6316de0bd85571f93d0c6bb5dfd5263a5b | utf-8-sig | PASS |  | 2026-10-30T12:00:03+05:30
tools/sat/acceptance.py | test-tooling | 8782 | 241 | 46c432833c79426d48e8db6c5dd2132122d00d72ef070f71b7c770b7af9577e1 | utf-8-sig | PASS |  | 2026-10-30T12:03:57+05:30
tools/sat/auto_heal.py | test-tooling | 21207 | 487 | 25422476bfc31261b9dfaab502c9f54ad6012009426fda320a94f5367ec1d81a | utf-8-sig | PASS |  | 2026-10-30T12:30:18+05:30
tools/sat/build_check.py | test-tooling | 11565 | 305 | 87d663b65c67360adf4f6861c8fb32b8c733cc5519b76bb81da998521fc33efe | utf-8-sig | PASS |  | 2026-10-30T12:32:38+05:30
tools/sat/common.py | test-tooling | 16140 | 508 | efd582d16918bf7f8a6e628d1b0864ea040f496b6f2f07fbaf9bab18d71215fe | utf-8-sig | PASS |  | 2026-10-30T12:18:51+05:30
tools/sat/config.json | test-tooling | 4132 | 110 | 1b21310907a963e7bfb3c65e34d4a1eafa11740a6e0606a14b552f879c732b5b | utf-8-sig | PASS |  | 2026-10-30T12:04:44+05:30
tools/sat/cpp_tests/test_common.cpp | test-tooling | 7138 | 189 | 883eb2521edb3d5f3e5e308c2c8c97c88311d39c071d3496d8b7838113d5e83a | utf-8-sig | PASS |  | 2026-10-30T12:08:18+05:30
tools/sat/excel_report.py | test-tooling | 26333 | 553 | 11629c1768ee46c43be3ded6e98f53899d29a7464580d0a6d200e5a71249b4bd | utf-8-sig | PASS |  | 2026-10-30T12:05:03+05:30
tools/sat/integration_check.py | test-tooling | 40202 | 800 | f9b032340ea8c77fed7413148cf95699feb9d4b48357e85a1786836cc058a082 | utf-8-sig | PASS |  | 2026-10-30T12:21:38+05:30
tools/sat/inventory.py | test-tooling | 12097 | 297 | 6188185e010d5065f633b7cf35afa4190cc17495aa3bb46f0ceda7f1d0a9de83 | utf-8-sig | PASS |  | 2026-10-30T12:06:40+05:30
tools/sat/pipeline.py | test-tooling | 4237 | 112 | 6dc5cf3d6f487b79316672dca7b32fff0716c12d314f3c3ceba81bf0b6f6a801 | utf-8-sig | PASS |  | 2026-10-30T11:59:59+05:30
tools/sat/protocol_client.py | test-tooling | 6689 | 187 | 4b7137e75e42e4bbd133387f5a3384eb51ac4149ff29a156a241e1e30e0e1029 | utf-8-sig | PASS |  | 2026-10-30T11:52:09+05:30
tools/sat/release_push.py | test-tooling | 10837 | 285 | 1ba5d07f8d7ef829187de280630aa41388506d7ae18b5b10db76bbeb550b1f67 | utf-8-sig | PASS |  | 2026-10-30T12:28:41+05:30
tools/sat/sat_runner.py | test-tooling | 15617 | 332 | 0d91bf91cdcf3b7325fa3870b8dd4c3724fad1638af9c6e3d32492ed03f658f3 | utf-8-sig | PASS |  | 2026-10-30T12:26:59+05:30
tools/sat/static_checks.py | test-tooling | 32411 | 732 | b94ebc87f22d0419c1d58d0b8b5d9c826a29e7ea16cce0b5799046298ab7ecd3 | utf-8-sig | PASS |  | 2026-10-30T12:06:40+05:30
tools/sat/unit_check.py | test-tooling | 5733 | 152 | 2b9ea3a4fa49fee0fdf5d419ad23c9cd4f1b7b1510d7bc3121346efee2083405 | utf-8-sig | PASS |  | 2026-10-30T12:08:27+05:30
vcpkg.json | repository | 130 | 8 | c306047d9647dbefb41a3a29527651dfb568d82ca53da98d7bb292e958351b48 | utf-8-sig | PASS |  | 2026-10-22T09:51:12+05:30

## Build Log
Build Log
MSBuild output and parsed compiler diagnostics.
Kind | File | Line | Code | Severity | Message
WARNING | C:\vcpkg\installed\x64-windows\include\hiredis\sds.h | 59 | C4200 | Minor | nonstandard extension used: zero-sized array in struct/union [C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\ChatServer\ChatServer.vcxproj]
WARNING | C:\vcpkg\installed\x64-windows\include\hiredis\sds.h | 65 | C4200 | Minor | nonstandard extension used: zero-sized array in struct/union [C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\ChatServer\ChatServer.vcxproj]
WARNING | C:\vcpkg\installed\x64-windows\include\hiredis\sds.h | 71 | C4200 | Minor | nonstandard extension used: zero-sized array in struct/union [C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\ChatServer\ChatServer.vcxproj]
WARNING | C:\vcpkg\installed\x64-windows\include\hiredis\sds.h | 77 | C4200 | Minor | nonstandard extension used: zero-sized array in struct/union [C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\ChatServer\ChatServer.vcxproj]
WARNING | C:\vcpkg\installed\x64-windows\include\hiredis\sds.h | 83 | C4200 | Minor | nonstandard extension used: zero-sized array in struct/union [C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\ChatServer\ChatServer.vcxproj]
RAW BUILD OUTPUT (tail)
Command: C:\Program Files\Microsoft Visual Studio\18\Community\MSBuild\Current\Bin\MSBuild.exe C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\CppChatMessaging.sln /t:Rebuild /p:Configuration=Release /p:Platform=x64 /p:VCPKG_ROOT=C:\vcpkg /m /v:minimal /nologo Exit code: 0 Duration: 42892 ms Timed out: False ------------------------------------------------------------------------------ The vcpkg manifest was disabled, but we found a manifest file in C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\. You may want to enable vcpkg manifests in your properties page or pass /p:VcpkgEnableManifest=true to the msbuild invocation. ChatClient.cpp _WIN32_WINNT not defined. Defaulting to _WIN32_WINNT_MAXVER (see WinSDKVer.h) The vcpkg manifest was disabled, but we found a manifest file in C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\. You may want to enable vcpkg manifests in your properties page or pass /p:VcpkgEnableManifest=true to the msbuild invocation. The vcpkg manifest was disabled, but we found a manifest file in C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\. You may want to enable vcpkg manifests in your properties page or pass /p:VcpkgEnableManifest=true to the msbuild invocation. The vcpkg manifest was disabled, but we found a manifest file in C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\. You may want to enable vcpkg manifests in your properties page or pass /p:VcpkgEnableManifest=true to the msbuild invocation. main.cpp main.cpp main.cpp LoadBalancer.cpp RedisCache.cpp DatabaseWriter.cpp C:\vcpkg\installed\x64-windows\include\hiredis\sds.h(59,10): warning C4200: nonstandard extension used: zero-sized array in struct/union [C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\ChatServer\ChatServer.vcxproj] (compiling source file 'RedisCache.cpp') C:\vcpkg\installed\x64-windows\include\hiredis\sds.h(59,10): This member will be ignored by a defaulted constructor or copy/move assignment operator C:\vcpkg\installed\x64-windows\include\hiredis\sds.h(65,10): warning C4200: nonstandard extension used: zero-sized array in struct/union [C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\ChatServer\ChatServer.vcxproj] (compiling source file 'RedisCache.cpp') C:\vcpkg\installed\x64-windows\include\hiredis\sds.h(65,10): This member will be ignored by a defaulted constructor or copy/move assignment operator C:\vcpkg\installed\x64-windows\include\hiredis\sds.h(71,10): warning C4200: nonstandard extension used: zero-sized array in struct/union [C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\ChatServer\ChatServer.vcxproj] (compiling source file 'RedisCache.cpp') C:\vcpkg\installed\x64-windows\include\hiredis\sds.h(71,10): This member will be ignored by a defaulted constructor or copy/move assignment operator C:\vcpkg\installed\x64-windows\include\hiredis\sds.h(77,10): warning C4200: nonstandard extension used: zero-sized array in struct/union [C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\ChatServer\ChatServer.vcxproj] (compiling source file 'RedisCache.cpp') C:\vcpkg\installed\x64-windows\include\hiredis\sds.h(77,10): This member will be ignored by a defaulted constructor or copy/move assignment operator C:\vcpkg\installed\x64-windows\include\hiredis\sds.h(83,10): warning C4200: nonstandard extension used: zero-sized array in struct/union [C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\ChatServer\ChatServer.vcxproj] (compiling source file 'RedisCache.cpp') C:\vcpkg\installed\x64-windows\include\hiredis\sds.h(83,10): This member will be ignored by a defaulted constructor or copy/move assignment operator ChatSession.cpp KafkaConsumer.cpp BackendManager.cpp ServerConfig.cpp TcpServer.cpp TcpProxy.cpp Ini.cpp LoginDlg.cpp Ini.cpp JsonUtil.cpp _WIN32_WINNT not defined. Defaulting to _WIN32_WINNT_MAXVER (see WinSDKVer.h) UdpHeartbeat.cpp Logger.cpp JsonUtil.cpp Logger.cpp Protocol.cpp MySQLDatabase.cpp Protocol.cpp MainDlg.cpp _WIN32_WINNT not defined. Defaulting to _WIN32_WINNT_MAXVER (see WinSDKVer.h) Generating Code... KafkaProducer.cpp Generating Code... Ini.cpp JsonUtil.cpp GroupDlg.cpp _WIN32_WINNT not defined. Defaulting to _WIN32_WINNT_MAXVER (see WinSDKVer.h) Logger.cpp Protocol.cpp DBWriter.vcxproj -> C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\bin\Release\DBWriter.exe C:\vcpkg\installed\x64-windows\bin\rdkafka.dll -> C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\bin\Release\rdkafka.dll done C:\vcpkg\installed\x64-windows\bin\lz4.dll -> C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\bin\Release\lz4.dll done UiControls.cpp LoadBalancer.vcxproj -> C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\bin\Release\LoadBalancer.exe Sha256.cpp _WIN32_WINNT not defined. Defaulting to _WIN32_WINNT_MAXVER (see WinSDKVer.h) Generating Code... Ini.cpp JsonUtil.cpp Logger.cpp Protocol.cpp Sha256.cpp Generating Code... ChatServer.vcxproj -> C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\bin\Release\ChatServer.exe C:\vcpkg\installed\x64-windows\bin\hiredis.dll -> C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\bin\Release\hiredis.dll done ChatClient.vcxproj -> C:\Users\Asus\OneDrive\Documents\Default Project\DualThread\bin\Release\ChatClient.exe

## Environment
Environment & Evidence
Host, toolchain, ports, git revision and integration run identifiers.
Category | Key | Value
SYSTEM
System | os | Windows 11
System | machine | AMD64
System | python | 3.13.15
System | executable | C:\Users\Asus\AppData\Local\Programs\Python\Python313\python.exe
System | cwd | C:\Users\Asus\OneDrive\Documents\Default Project\DualThread
System | project | C:\Users\Asus\OneDrive\Documents\Default Project\DualThread
System | user | Asus
System | hostname | LAPTOP-8FR2FME0
PORTS
Port | mysql | listening
Port | redis | listening
Port | kafka | listening
Port | loadbalancer_tcp | listening
Port | loadbalancer_udp | not listening
Port | server1_tcp | listening
Port | server1_udp | not listening
Port | server2_tcp | listening
Port | server2_udp | not listening
GIT
Git | branch | main
Git | commit | 135c642
Git | dirty | TRUE
Git | remote | https://github.com/Tamilselvan-19/DualThread.git
INTEGRATION RUN
Integration | run_id | SAT-20261030-125247-0f29d0
Integration | server_ids | server1, server2
Integration | message_count | 2
TEST PARAMETERS
Arguments | project | C:\Users\Asus\OneDrive\Documents\Default Project\DualThread
Arguments | config
Arguments | mode | full
Arguments | full | TRUE
Arguments | skip_build | FALSE
Arguments | skip_unit | FALSE
Arguments | skip_integration | FALSE
Arguments | skip_ui | FALSE
Arguments | no_excel | FALSE
Arguments | output_dir
Arguments | tag
Run | duration_seconds | 92.8
Run | tag

## Traceability
Requirement Traceability
Each documented capability mapped to source evidence and executed checks.
Requirement ID | Requirement | Code Evidence | Runtime Evidence | Status | Runtime Required
REQ-01 | Personal messaging across two servers | ChatServer/TcpServer.cpp; ChatClient/ChatSession.cpp | INT-018; INT-022 | PASS | yes
REQ-02 | Group creation, membership and group messaging | ChatServer/TcpServer.cpp; ChatServer/TcpServer.cpp; database/schema.sql | INT-020; INT-021; INT-022 | PASS | yes
REQ-03 | Online/offline presence | ChatServer/TcpServer.cpp; ChatClient/MainDlg.cpp | INT-015; INT-021 | PASS | yes
REQ-04 | Typing indicator | ChatServer/TcpServer.cpp; ChatClient/MainDlg.cpp | INT-019 | PASS | yes
REQ-05 | Unread badges with previews | ChatClient/MainDlg.cpp; ChatClient/UiControls.cpp | INT-038 | PASS | no
REQ-06 | Server-side history (last 100 messages) | ChatServer/TcpServer.cpp; ChatServer/MySQLDatabase.cpp | INT-023; INT-024 | PASS | yes
REQ-07 | Automatic reconnection with backoff | ChatClient/ChatSession.cpp; ChatClient/MainDlg.cpp | INT-037 | PASS | yes
REQ-08 | UDP heartbeat and RTT monitoring | ChatServer/UdpHeartbeat.cpp; LoadBalancer/LoadBalancer.cpp | INT-025 | PASS | yes
REQ-09 | Redis auth cache, presence and Pub/Sub routing | ChatServer/TcpServer.cpp; ChatServer/RedisCache.cpp | INT-016; INT-017; INT-018 | PASS | yes
REQ-10 | Kafka event pipeline | ChatServer/KafkaProducer.cpp; DBWriter/KafkaConsumer.cpp | INT-033; INT-034; INT-035 | PASS | yes
REQ-11 | MySQL persistence through DBWriter | DBWriter/DatabaseWriter.cpp; database/schema.sql | STR-023; STR-024; INT-023; INT-034; INT-035 | PASS | yes
REQ-12 | Round-robin load balancing and health checks | LoadBalancer/BackendManager.cpp; LoadBalancer/BackendManager.cpp | INT-014 | PASS | yes
REQ-13 | Native MFC desktop UI | ChatClient/ChatClient.cpp; ChatClient/ChatClient.vcxproj | INT-038 | PASS | yes
REQ-14 | Input validation and injection resistance | ChatServer/TcpServer.cpp; ChatServer/MySQLDatabase.cpp | INT-026; INT-027; INT-028; INT-029; INT-030 | PASS | yes
REQ-15 | Reproducible Release¦x64 build and deployment | CppChatMessaging.sln; scripts/start-all.ps1 | ENV-004; ENV-005; BLD-001; BLD-002; BLD-003; BLD-004; BLD-005; BLD-006; BLD-007 | PASS | yes

## Release Manifest
Release Manifest
Executables and runtime DLLs tested in this run.
Artifact | Kind | Path | Bytes | Architecture | SHA-256 | Valid | Modified
ChatClient.exe | executable | bin/Release/ChatClient.exe | 715776 | x64 | cc37f3d8952a6ca370c8dee63772cbf553d21f1f03b8d8d7d76a1c2eb9491a31 | yes | 2026-10-30T12:52:34+05:30
ChatServer.exe | executable | bin/Release/ChatServer.exe | 672256 | x64 | c5ac2b666ad5251b64f5c4be6a9896652e9adf63b02adf0afbf718e60aa5b15b | yes | 2026-10-30T12:52:30+05:30
LoadBalancer.exe | executable | bin/Release/LoadBalancer.exe | 483840 | x64 | afba2be68c6ad7741ecce670aca444c82a8a999d9cfbb8c24350482afc953190 | yes | 2026-10-30T12:52:15+05:30
DBWriter.exe | executable | bin/Release/DBWriter.exe | 464896 | x64 | ae9303a54c562167b78a71140562843a11dda62b358a4676d1972492702763e4 | yes | 2026-10-30T12:52:13+05:30
hiredis.dll | runtime-dll | bin/Release/hiredis.dll | 120832 | x64 | 2026682b3031cc63f90d4a6ab45962370587f34288d3f94d3db61024b7c358f4 | yes | 2026-10-21T18:28:59+05:30
rdkafka.dll | runtime-dll | bin/Release/rdkafka.dll | 2398208 | x64 | 6ba3e8ca451449949837fa3861a3646f18e6fffd6961992a79a0331de3d65e30 | yes | 2026-10-07T22:36:23+05:30
lz4.dll | runtime-dll | bin/Release/lz4.dll | 130048 | x64 | d029d2e9cb7ca8433e3f5d1a0717d3f026d79054956612cd7fdf4052d2d99738 | yes | 2026-10-07T22:35:01+05:30

## Heal Log
Auto-Heal Log
Changes proposed or applied by the auto-healer agent.
Timestamp | Iteration | Action | Test ID | File | Result | Details
2026-10-30T12:29:09+05:30 | 1 | invoke-agent |  |  | invoked | {"invoked": true, "binary": "definitely-not-opencode", "ok": false, "code": -1, "stdout": "", "stderr": "FileNotFoundError: [WinError 2] The system cannot find the file specified", "duration_ms": 44}
2026-10-30T12:30:03+05:30 | 1 | rebuild |  |  | ok | {"ok": true, "log": "C:\\Users\\Asus\\OneDrive\\Documents\\Default Project\\DualThread\\reports\\logs\\build-20261030-123003.log", "errors": 0, "warnings": 5}

## Run History
Run History
The most recent SAT runs in this workspace.
Report | Started | Mode | Gate | Total | Passed | Failed | Warnings | Pass Rate
sat-results-latest.json | 2026-10-30T12:51:41+05:30 | full | PASS | 163 | 161 | 0 | 2 | 98.77
sat-results-20261030-125141.json | 2026-10-30T12:51:41+05:30 | full | PASS | 163 | 161 | 0 | 2 | 98.77
sat-results-20261030-123248.json | 2026-10-30T12:32:48+05:30 | full | PASS | 163 | 160 | 0 | 3 | 98.16
sat-results-20261030-123028.json | 2026-10-30T12:30:28+05:30 | full | PASS | 163 | 160 | 0 | 3 | 98.16
sat-results-20261030-122710.json | 2026-10-30T12:27:10+05:30 | full | PASS | 157 | 155 | 0 | 2 | 98.73
sat-results-20261030-122527.json | 2026-10-30T12:25:27+05:30 | full | PASS | 157 | 155 | 0 | 2 | 98.73
sat-results-20261030-122217.json | 2026-10-30T12:22:17+05:30 | full | PASS | 163 | 161 | 0 | 2 | 98.77
sat-results-20261030-121917.json | 2026-10-30T12:19:17+05:30 | full | FAIL | 163 | 158 | 2 | 3 | 96.93
sat-results-20261030-120832.json | 2026-10-30T12:08:32+05:30 | build | PASS | 118 | 102 | 0 | 15 | 87.18
sat-results-20261030-120646.json | 2026-10-30T12:06:46+05:30 | build | FAIL | 82 | 64 | 1 | 16 | 79.01
sat-results-20261030-120605.json | 2026-10-30T12:06:05+05:30 | quick | PASS | 77 | 60 | 0 | 15 | 80
sat-results-20261030-120509.json | 2026-10-30T12:05:09+05:30 | quick | PASS | 77 | 59 | 0 | 16 | 78.67
sat-results-20261030-120403.json | 2026-10-30T12:04:03+05:30 | quick | PASS | 77 | 57 | 0 | 18 | 76
sat-results-20261030-120252.json | 2026-10-30T12:02:52+05:30 | quick | FAIL | 77 | 55 | 3 | 17 | 73.33